## 12-2018
Trust Fund Utilization
CONSOLIDATED REPORT ON GOVERNMENT PROJECTS, PROGRAMS or ACTIVITIES
12/31/2018
San Pablo City
|  |  |  | Target | Project Status |  | No. of
Projects/Programs | Location | Total Cost | Date Started | Completion | % of | Total Cost Incurred | Extensions,if | Remarks
|  |  |  | Date | Completion | to Date | any
Supplemental Feeding Program | DSWD | 7515000 | 2017-07-14 | 2018-05-31 | 100% | 7515000 |  | Completed and Liquidated
Supplemental Feeding Program | DSWD | 8168400 | 2018-08-01 | 2019-03-31 | 67% | 5524315 |  | On - going
Provision of Toilet bowls and water | BUB Project 2016 | 1000000 |  | 2018-03-12 | 100% | 1000000 |  | Completed and Liquidated
sampling | DOH
TUPAD and KABUHAYAN Program | DOLE Region IV-A | 2973020 | 2017-07-01 |  | 100% | 2973020 |  | Completed and Liquidated
SDG FACES Project | DILG-Region IV-A | 50000 |  |  | 100% | 50000 |  | Transfer to General Fund/Project Completed
DSWD Social Pension Program | DSWD IV-A | 3000000 | 2018-02-27 | 2018-03-31 | 100% | 3000000 |  | Completed and Liquidated
DSWD Social Pension Program | DSWD IV-A | 3000000 | 2018-05-18 | 2018-06-30 | 100% | 3000000 |  | Completed and Liquidated
DSWD Social Pension Program | DSWD IV-A | 3000000 | 2018-08-01 | 2018-09-30 | 100% | 3000000 |  | Completed and Liquidated
DSWD Social Pension Program | DSWD IV-A | 3000000 | 2018-11-02 | 2018-12-30 | 100% | 3000000 |  | Completed and Liquidated
DSWD Cash for Work | DSWD IV-A | 1158720 | 2018-12-12 | 2018-12-31 | 100% | 1158720 |  | Completed and Liquidated
Total |  | 32865140 |  |  |  | 30221055 | 0 | 0
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
LOLITA G.CORNISTA |  | Hon. LORETO S. AMANTE
City Accountant |  | City Mayor